## Gantt Chart
TASK | START DATE | DURATION | END DATE
Buy and assemble componenets of the System | 2016-10-11 | 5 | 2016-10-16
Setup infrastructure to allow for deployment of applications | 2016-10-16 | 7 | 2016-10-23
Create Basic Client Program to make web requests | 2016-10-23 | 4 | 2016-10-27
Create Basic Edge Server Program to return web response | 2016-10-27 | 6 | 2016-11-02
Create Data Centre program to return web responses | 2016-11-02 | 4 | 2016-11-06
Update Client Program Design | 2016-11-06 | 6 | 2016-11-12
Update Edge Server Program to receive web requests | 2016-11-12 | 2 | 2016-11-14
Update Edge Server Program to process web requests | 2016-11-14 | 6 | 2016-11-20
Update Data Centre Program to receive web requests | 2016-11-20 | 5 | 2016-11-25
Update Data Centre program to process web requests | 2016-11-25 | 2 | 2016-11-27
Update Client Program to handle responses | 2016-11-27 | 1 | 2016-11-28
Update Client Program to make multiple web requests | 2016-11-28 | 5 | 2016-12-03
Research and design caching application | 2016-12-03 | 2 | 2016-12-05
Create image for the cachine application | 2016-12-05 | 8 | 2016-12-13
Perform analysis and update caching application | 2016-12-13 | 14 | 2016-12-27
Research and design voice recognition application | 2016-12-27 | 16 | 2017-01-12
Create image for voice recognition application | 2017-01-12 | 5 | 2017-01-17
Perform analysis and update voice recognition application | 2017-01-17 | 14 | 2017-01-31
Research and design machine learning application | 2017-01-31 | 7 | 2017-02-07
Create image for machine learning application | 2017-02-07 | 7 | 2017-02-14
Perform analysis and update machine learning application | 2017-02-14 | 14 | 2017-02-28
Formulas:
END DATE = [START DATE]+[DURATION]
START DATE = [END DATE, row above]