## Gantt Chart
TASK | START DATE | DURATION | END DATE
Buy and assemble componenets of the System | 2016-10-11 | 5 | 2016-10-16
Setup infrastructure to allow for deployment of applications | 2016-10-16 | 7 | 2016-10-23
Create Edge Node Application | 2016-10-23 | 21 | 2016-11-13
Create Data Centre Application | 2016-11-01 | 13 | 2016-11-14
Create Client Application | 2016-10-30 | 19 | 2016-11-18
Research/design/create caching application | 2016-11-18 | 24 | 2016-12-12
Research/design/create voice recognition application | 2016-12-12 | 30 | 2017-01-11
Research/design/create machine learning application | 2017-01-11 | 50 | 2017-03-02
Perform analysis and update caching application | 2017-03-02 | 7 | 2017-03-09
Perform analysis and update voice recognition application | 2017-03-09 | 7 | 2017-03-16
Perform analysis and update machine learning application | 2017-03-16 | 7 | 2017-03-23
Research and implement efficient way to handle Edge Node resources | 2017-03-23 | 14 | 2017-04-06
Formulas:
END DATE = [START DATE]+[DURATION]
START DATE = [END DATE, row above]