## Gantt Chart
TASK | START DATE | DURATION | END DATE
Buy and assemble componenets of the System | 2016-10-11 | 5 | 2016-10-16
Setup infrastructure to allow for deployment of applications | 2016-10-16 | 7 | 2016-10-23
Create Basic Client Program | 2016-10-23 | 4 | 2016-10-27
Update Basic Client program to make web requests | 2016-10-27 | 6 | 2016-11-02
Create Basic Edge Server Program | 2016-11-02 | 4 | 2016-11-06
Update Edge Server program to return web response | 2016-11-06 | 6 | 2016-11-12
Create Data Centre program | 2016-11-12 | 2 | 2016-11-14
Update Data Centre program to return web responses | 2016-11-14 | 6 | 2016-11-20
Update Client Program Design | 2016-11-20 | 5 | 2016-11-25
Update Edge Server Program to receive web requests | 2016-11-25 | 2 | 2016-11-27
Update Edge Server Program to process web requests | 2016-11-27 | 1 | 2016-11-28
Update Data Centre Program to receive web requests | 2016-11-28 | 5 | 2016-12-03
Update Data Centre program to process web requests | 2016-12-03 | 2 | 2016-12-05
Update Client Program to handle responses | 2016-12-05 | 8 | 2016-12-13
Update Client Program to make multiple web requests | 2016-12-13 | 14 | 2016-12-27
| 2016-12-27 | 16 | 2017-01-12
| 2017-01-12 | 5 | 2017-01-17
| 2017-01-17 | 14 | 2017-01-31
| 2017-01-31 | 7 | 2017-02-07
Research and design caching application | 2017-02-07 | 7 | 2017-02-14
Create image for the cachine application | 2017-02-14 | 14 | 2017-02-28
Perform analysis and update caching application | 2017-02-28 | 14 | 2017-03-14
Research and design voice recognition application
Create image for voice recognition application
Perform analysis and update voice recognition application
Research and design machine learning application
Create image for machine learning application
Perform analysis and update machine learning application
Formulas:
END DATE = [START DATE]+[DURATION]
START DATE = [END DATE, row above]