## Gantt Chart
TASK | START DATE | DURATION | END DATE
Buy and assemble componenets of the System | 2016-10-11 | 5 | 2016-10-16
Setup infrastructure to allow for deployment of applications | 2016-10-16 | 7 | 2016-10-23
Create Basic Client Program to make web requests | 2016-10-23 | 4 | 2016-10-27
Create Basic Edge Server Program to return web response | 2016-10-27 | 6 | 2016-11-02
Create Data Centre program to return web responses | 2016-11-02 | 4 | 2016-11-06
Update Client Program Design | 2016-11-06 | 6 | 2016-11-12
Update Edge Server Program to receive web requests | 2016-11-12 | 2 | 2016-11-14
Update Edge Server Program to process web requests | 2016-11-14 | 6 | 2016-11-20
Update Data Centre Program to receive web requests | 2016-11-20 | 7 | 2016-11-27
Update Data Centre program to process web requests | 2016-11-27 | 2 | 2016-11-29
Update Client Program to handle responses | 2016-11-29 | 1 | 2016-11-30
Update Client Program to make multiple web requests | 2016-11-30 | 5 | 2016-12-05
Research and design caching application | 2016-12-05 | 7 | 2016-12-12
Create image for the cachine application | 2016-12-12 | 7 | 2016-12-19
Perform analysis and update caching application | 2016-12-19 | 14 | 2017-01-02
Research and design voice recognition application | 2017-01-02 | 7 | 2017-01-09
Create image for voice recognition application | 2017-01-09 | 7 | 2017-01-16
Perform analysis and update voice recognition application | 2017-01-16 | 14 | 2017-01-30
Research and design machine learning application | 2017-01-30 | 16 | 2017-02-15
Create image for machine learning application | 2017-02-15 | 7 | 2017-02-22
Perform analysis and update machine learning application | 2017-02-22 | 14 | 2017-03-08
Research efficient way to handle Edge Node resources | 2017-03-08 | 14 | 2017-03-22
Implement Edge Node resource handling | 2017-03-22 | 14 | 2017-04-05
Formulas:
END DATE = [START DATE]+[DURATION]
START DATE = [END DATE, row above]