## Gantt Chart
TASK | START DATE | DURATION | END DATE
Buy and assemble componenets of the System | 2016-10-11 | 5 | 2016-10-16
Setup infrastructure to allow for deployment of applications | 2016-10-16 | 7 | 2016-10-23
Create Basic Client program to make web requests | 2016-10-23 | 4 | 2016-10-27
Create Edge Server program to receive web requests | 2016-10-27 | 6 | 2016-11-02
Create Data Centre program to receive web requests | 2016-11-02 | 4 | 2016-11-06
Update Data Centre program to process web requests | 2016-11-06 | 6 | 2016-11-12
Update Data Centre program to return web responses | 2016-11-12 | 2 | 2016-11-14
Process web requests in the Edge Cluster | 2016-11-14 | 6 | 2016-11-20
Update Edge Server program to return web response | 2016-11-20 | 5 | 2016-11-25
Update Client Program to handle responses | 2016-11-25 | 2 | 2016-11-27
Design Client Program UI | 2016-11-27 | 1 | 2016-11-28
Update Client Program to match design | 2016-11-28 | 5 | 2016-12-03
Update Client Program to make multiple web requests | 2016-12-03 | 2 | 2016-12-05
Research and design caching application | 2016-12-05 | 8 | 2016-12-13
Create image for the cachine application | 2016-12-13 | 14 | 2016-12-27
Perform analysis and update caching application | 2016-12-27 | 16 | 2017-01-12
Research and design voice recognition application | 2017-01-12 | 5 | 2017-01-17
Create image for voice recognition application | 2017-01-17 | 14 | 2017-01-31
Perform analysis and update voice recognition application | 2017-01-31 | 7 | 2017-02-07
Research and design machine learning application | 2017-02-07 | 7 | 2017-02-14
Create image for machine learning application | 2017-02-14 | 14 | 2017-02-28
Perform analysis and update machine learning application | 2017-02-28 | 14 | 2017-03-14
Formulas:
END DATE = [START DATE]+[DURATION]
START DATE = [END DATE, row above]